## Sheet1
Epic | Story ID | Story Title | Description | Priority | Story Points | Status | Acceptance Criteria | Business Value | Dependencies
Authentication | US001 | Admin Menu System | Develop menu system for admin operations | High | 8 | Done | Menu displays after successful login, handles all 9 options, proper error handling | High
User Management | US002 | Customer Registration | Allow customers to register accounts | High | 5 | Done | Unique customer ID generation, email validation, password complexity, phone validation | High
User Management | US003 | Update Customer Details | Allow customers to update their information | Medium | 3 | Done | Authentication required, field validation, successful update confirmation | Medium | US002
Order Management | US004 | Get Customer Order Details | Display customer order history | High | 5 | Done | Customer authentication, order history display, proper data formatting | High | US002
Admin Features | US005 | Search Customer Details | Admin can search customers by name | Medium | 3 | Done | Admin authentication, case-insensitive search, proper error handling | Medium | US001
Product Catalog | US006 | Search Product Details | Customers can search products | High | 3 | Done | Product search functionality, case-insensitive, availability check | High
Product Management | US007 | Register Product | Admin can add new products | High | 5 | Done | Product validation, unique ID generation, price and quantity validation | High | US001
Product Management | US008 | Update Product | Admin can modify product details | Medium | 3 | Done | Product exists validation, field validation, successful update | Medium | US007
Product Management | US009 | Delete Product | Admin can remove products | Low | 2 | Done | Product exists validation, confirmation dialog, successful deletion | Low | US007
Security | US010 | SQL Injection Prevention | Prevent SQL injection attacks | Critical | 8 | Done | All queries use prepared statements, input validation, security testing | Critical | All Stories
Frontend | FE001 | Angular Customer Portal | Modern web interface for customers | High | 13 | Done | Responsive design, intuitive navigation, real-time updates | High | US002 US004 US006
Admin Interface | AI001 | JSP Admin Dashboard | Server-side admin interface | High | 8 | Done | Complete admin functionality, secure access, professional UI | High | US001 US005 US007 US008 US009
Infrastructure | INF001 | Database Setup | MySQL database with Docker | High | 5 | Done | Complete schema, sample data, proper constraints, Docker containerization | High | All Stories
Infrastructure | INF002 | Spring Boot Backend | RESTful API backend | High | 10 | Done | Complete REST APIs, proper error handling, security integration | High | All Stories
Security | SEC001 | Authentication System | Secure login and session management | Critical | 8 | Done | BCrypt encryption, session management, role-based access | Critical | US001 US002
Security | SEC002 | Authorization System | Role-based access control | High | 5 | Done | Admin and customer roles, proper access restrictions | High | SEC001
Performance | PER001 | Database Optimization | Optimize database performance | Medium | 3 | Done | Proper indexing, connection pooling, query optimization | Medium | INF001
Quality | QUA001 | Code Quality | Maintain high code quality standards | Medium | 5 | Done | Clean architecture, proper documentation, error handling | Medium | All Stories
Documentation | DOC001 | Technical Documentation | Comprehensive project documentation | Low | 3 | Done | README, API docs, user manual, NFRs documentation | Low | All Stories
Testing | TEST001 | System Testing | Comprehensive testing strategy | Medium | 5 | Done | Unit tests, integration tests, manual testing | Medium | All Stories