## Sheet1
Issue ID | Category | Type | Title | Description | Severity | Priority | Status | Found Date | Resolved Date | Found By | Assigned To | Module | Resolution | Impact
QUA-001 | Security | SQL Injection | Potential SQL injection vulnerability | Raw SQL queries without parameterization | Critical | Critical | Closed | 2025-08-01 | 2025-08-01 | Chirag Singhal | Chirag Singhal | Database Layer | Replaced all raw queries with prepared statements | High - Prevents data breaches
QUA-002 | Security | Authentication | Weak password policy | Password requirements not enforced | High | High | Closed | 2025-08-01 | 2025-08-01 | Chirag Singhal | Chirag Singhal | Authentication | Implemented strong password validation with regex | Medium - Improves account security
QUA-003 | Security | Session Management | Session fixation vulnerability | Session ID not regenerated after login | Medium | High | Closed | 2025-08-01 | 2025-08-01 | Chirag Singhal | Chirag Singhal | Security Config | Configured session fixation protection in Spring Security | Medium - Prevents session attacks
QUA-004 | Security | Headers | Missing security headers | Security headers not configured | Medium | Medium | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Security Config | Added comprehensive security headers configuration | Medium - Improves browser security
QUA-005 | Security | CSRF | CSRF protection not enabled | Cross-site request forgery protection missing | High | High | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Security Config | Enabled CSRF protection for form submissions | High - Prevents CSRF attacks
QUA-006 | Code Quality | Architecture | Tight coupling between layers | Direct database access from controllers | Medium | Medium | Closed | 2025-08-01 | 2025-08-01 | Chirag Singhal | Chirag Singhal | Architecture | Implemented proper layered architecture with services | Medium - Improves maintainability
QUA-007 | Code Quality | Exception Handling | Inconsistent error handling | Different exception handling patterns | Low | Medium | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Error Handling | Standardized exception handling with global handlers | Low - Improves code consistency
QUA-008 | Code Quality | Validation | Missing input validation | Some endpoints lack proper validation | High | High | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Validation | Added comprehensive validation annotations | High - Prevents invalid data
QUA-009 | Code Quality | Documentation | Missing method documentation | Some methods lack proper Javadoc | Low | Low | Closed | 2025-08-03 | 2025-08-03 | Chirag Singhal | Chirag Singhal | Documentation | Added comprehensive Javadoc comments | Low - Improves code readability
QUA-010 | Code Quality | Constants | Magic numbers in code | Hard-coded values without constants | Low | Low | Closed | 2025-08-03 | 2025-08-03 | Chirag Singhal | Chirag Singhal | Code Quality | Replaced magic numbers with named constants | Low - Improves code maintainability
QUA-011 | Performance | Database | Missing database indexes | Queries without proper indexing | Medium | Medium | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Database | Added indexes on frequently queried columns | Medium - Improves query performance
QUA-012 | Performance | Connection Pool | Suboptimal connection pool settings | Default connection pool configuration | Low | Medium | Closed | 2025-08-02 | 2025-08-02 | Chirag Singhal | Chirag Singhal | Database Config | Optimized HikariCP connection pool settings | Low - Improves resource utilization
QUA-013 | Usability | UI | Inconsistent error messages | Different error message formats | Low | Low | Closed | 2025-08-03 | 2025-08-03 | Chirag Singhal | Chirag Singhal | Frontend | Standardized error message display | Low - Improves user experience
QUA-014 | Usability | Navigation | Missing breadcrumbs | No navigation breadcrumbs in admin panel | Low | Low | Open | 2025-08-03 |  | Chirag Singhal | Chirag Singhal | Admin UI | Future enhancement | Low - Would improve navigation
QUA-015 | Maintainability | Testing | Limited test coverage | Unit tests not comprehensive | Medium | Medium | Open | 2025-08-03 |  | Chirag Singhal | Chirag Singhal | Testing | Future enhancement - add more unit tests | Medium - Would improve code reliability