## Sheet1
Sprint | Story ID | Story Title | Story Points | Status | Assigned To | Start Date | End Date | Acceptance Criteria Met | Comments
Sprint 1 | US001 | Online Grocery Ordering Menu System | 8 | Completed | Chirag Singhal | 2025-08-01 | 2025-08-01 | Yes | Admin menu system with all options implemented
Sprint 1 | US002 | Customer Registration | 5 | Completed | Chirag Singhal | 2025-08-01 | 2025-08-01 | Yes | Registration with validation and unique customer ID generation
Sprint 1 | US003 | Update Customer Details | 3 | Completed | Chirag Singhal | 2025-08-01 | 2025-08-01 | Yes | Customer can update their profile information
Sprint 1 | US010 | SQL Injection Prevention | 8 | Completed | Chirag Singhal | 2025-08-01 | 2025-08-01 | Yes | All queries use prepared statements
Sprint 2 | US004 | Get Customer Order Details | 5 | Completed | Chirag Singhal | 2025-08-02 | 2025-08-02 | Yes | Customers can view their order history
Sprint 2 | US005 | Search Customer Details | 3 | Completed | Chirag Singhal | 2025-08-02 | 2025-08-02 | Yes | Admin can search customers by name
Sprint 2 | US006 | Search Product Details | 3 | Completed | Chirag Singhal | 2025-08-02 | 2025-08-02 | Yes | Customers can search products by name
Sprint 3 | US007 | Register Product | 5 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Admin can register new products
Sprint 3 | US008 | Update Product | 3 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Admin can update product details
Sprint 3 | US009 | Delete Product | 2 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Admin can delete products
Sprint 3 | Frontend Development | Angular Frontend Implementation | 13 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Complete Angular frontend with responsive design
Sprint 3 | Admin Dashboard | JSP Admin Dashboard | 8 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Complete admin dashboard with all management features
Sprint 3 | Security Implementation | Comprehensive Security Features | 8 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Authentication authorization and security headers
Sprint 3 | Database Setup | MySQL Database with Docker | 5 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | Complete database schema with sample data
Sprint 3 | Documentation | Project Documentation | 5 | Completed | Chirag Singhal | 2025-08-03 | 2025-08-03 | Yes | README CHANGELOG and technical documentation